Development of learning resources and 
student accommodation

Date completed: 18 March 2013

Background and context

The Cohuna District Hospital (CDH) is an acute rural hospital that accommodates students from universities in Victoria and South Australia. Although relatively small CDH offers students a variety of clinical experiences including general surgery, orthopaedic and gynaecological surgery, acute medical aged care and obstetrics. Students attending CDH traditionally report having a very positive, educational placement.

Participation in this project has enabled CDH to further support students by enabling purchase of up to date text books and printed resources for our library.

The purchase of four computers and a data projector ensures that students have access to dedicated student computers and online services including internet resources assist students to maintain contact with their educational institutions whilst on placement as well as assist educators with equipment for PowerPoint presentations.

CDH are one of a number of facilities that still provide accommodation to visiting students. The project facilitated minor works and refurbishment to existing accommodation to ensure a modicum of comfort for students using our accommodation.

Project objectives and expected impacts

To increase learner satisfaction with the quality and accessibility of educational resources provided at CDH

To increase learner satisfaction with the quality and accessibility of accommodation provided at CDH

To increase learner satisfaction with the clinical learning experience offered at CDH

Project activities

Improvements to accommodation included painting, window furnishings, air conditioners, beds, mattresses and cupboards

Laptop computer and data projector for education presentations were purchased instead of a second computer trolley

Project management

Governance

This project was managed by the Clinical Nurse Consultant at CDH in consultation with the CEO and Director of Nursing.

Stakeholder engagement and consultations

La Trobe University were consulted in addition to liaison with students about what learning resources they would like to see available to students at CDH. All students on placement at CDH now have the opportunity to access the up to date learning resources and improved accommodation facilities.

Budget

The project was completed slightly under budget.

Timelines

The project has been delivered within the specified project period and reporting deadlines have consistently been met during the project period. Where there have been delays these have been reported and subsequently caught up in later reporting periods.

Project performance against stated deliverables

| Project activity | Project deliverable/target | Due date | Status |
| --- | --- | --- | --- |
| Purchase and installation of equipment | Progress report with receipts demonstrating purchase and installation of equipment | 30 December 2012 | Completed |
| Improvements to student accommodation preliminaries completed | Quotes for painting window furnishings and air conditioning | 30 July 2012 | Completed |
| Completion of accommodation renovations | Progress report with tax invoice for work completed | September 2012 | Completed |
| Evaluation of the project in relation to project objectives and expected impacts | Progress report with evidence of achievement of objectives/ expected impacts | 1 April 2013 | Completed |

Learner satisfaction has increased with the quality and accessibility of educational resources provided through the project.

There is now access to a designated room where the new computers have been installed and up-to-date text books are located.

The improvements to the accommodation will ensure satisfaction and comfort with the air-conditioners and new beds. (The beds have just arrived and will be installed as soon as possible).

Project outcomes

New teaching opportunities are enabled with the use of the new laptop and data projector that can be easily moved to any location for education presentations.

Evaluation

Improved facilities and resources for students creating a better more productive placement

The project was achieved slightly under budget

The most difficult aspect was trying to predict the cost of individual items at the time of submission

The key learning from this program was that we needed more time to evaluate our requirements prior to lodging the submission.

Conclusion

Future students will benefit from the improvements made possible through this grant

Educators are now able to access up to date resources as teaching tools.

# Text boxes

Final report

Small Capital and Equipment Program