Gippsland South Coast enhanced public/private interprofessional student capacity project

Date: 1 May 2013
Reporting period: Quarterly project 5

Author: Ward Steet, BCRH Director of Community Services
Email: ward.steet@bcrh.com.au

# Brief overview of project

The project aims to provide suitable accommodation and a suitable learning space for undergraduate students from a range of health professions including medicine, nursing and allied health (physiotherapy, speech pathology, occupational therapy, dietetics, podiatry, social work, welfare work, aged care PCA’s, exercise physiology) to facilitate increased capacity for student placements in shared arrangements/partnerships between Bass Coast Regional Health (BCRH) and other ‘non-public acute’ organisations in expanded settings such as community health, home-based community care and aged care. The project will also pilot an innovative videoconferencing model of supervision and support for both student and clinical instructor utilising telemedicine principles as the platform.

# Project management/governance, including staff changes

The new Domain Seahaven representative for the project is the recently appointed Facility Manager, Ms. Robyn Broms.

# Progress against project deliverables

# Reporting requirement 1: Project activities

| Project activity | Project deliverable/target | Due date | Status (i.e., complete, in progress, yet to commence) |
| --- | --- | --- | --- |
| Establish Steering Committee | The Steering Committee in the form of the PCG has been established | February 2012 | Complete |
| Develop agreement on student placements and supervision | Agreement committing each agency to the proposed model of supervision and mentoring | March 2012 | Complete |
| RFQ for learning space works | Quotes assessed and builder appointed | February 2012 | Complete |
| Construction works for learning space | Learning space established and available to students while on placement | Commence construction April 2012; completion October 2012 | Complete |
| RFQ for student accommodation works | Student accommodation refurbished and ready for use by students on placement | Construction commencement April 2012; completion October 2012 | Complete |
| Purchase videoconferencing equipment for Domain Seahaven Aged Care | Videoconferencing facilities available to facilitate supervision of students and mentoring for clinical instructors | Purchase March 2012; Operational May 2012 | Complete |
| Capacity and capability established to facilitate undergraduate student placements in expanded setting | Capacity for at least undergraduate clinical places to be available at a time in the expanded setting | October 2012 in readiness for the 2013 clinical placements | Complete |
| Pilot and evaluate shared placement model | Pilot evaluation report | December 2012 | Completed |
| Evaluation | Evaluation report | January 2013 | Completed |

Progress and evaluation

The Gippsland South Coast enhanced public/private interprofessional student capacity project, auspiced by Bass Coast Regional Health has now been completed and evaluated. The project has managed to meet all the deliverables of the project. A key achievement of the project is the networks and relationships that have been developed during the project that makes the framework of the project and the objective of increased student clinical placement capacity in the region sustainable into the future.

The student learning space was officially opened in October 2012.The space has been well utilised by students from nursing, medicine and allied health disciplines, recording 206.5 hours of use over 198 occasions as at 1 May 2013. Many students have used the area after hours through to the early hours of the morning and over weekends for study and preparation for examinations. The videoconferencing equipment in the room has been utilised for multidisciplinary lectures/training/supervision which have been streamed to Gippsland Southern Health Service, Bass Coast Community Health Service and South Gippsland Hospital. As part of the refurbishment of the learning space BCRH was able to capitalise on the works to remove a wall between two existing education rooms and replace it with an operable wall creating capacity for education tutorials of up to 50 participants and significantly more room to use the area for simulation. This has value added to the project and significantly improved the education complex.

BCRH has 26 student orientation programs booked for 2013. BCRH has offered universities a total 128 aged care nursing student places for 2012-13. In addition it has offered 80 acute nursing student placements with new clinical placements being offered in ED and Theatre which has not occurred before now. This is a total of 208 nursing placements. Clinical placements for 2013 have commenced. BCRH Allied Health placement offers have been finalised. Podiatry has had their first student and further placements are booked.

Domain Seahaven applied through viCPlace for four nursing aged care students at a time over eight rotations for a total of 32 student placements. Supervision was planned be via videoconference and onsite visits by BCRH supervisors twice weekly. Unfortunately metropolitan CPN’s engaging in widespread Expanded Care Setting projects which have led to a dramatic decrease in the requests for rural aged care placements resulting in only one of the places offered by Seahaven being taken up and this placement was subsequently cancelled by the education provider. Subsequently, while capacity is there, the pilot distance supervision model, or remote facilitation, utilising videoconferencing equipment has not been tested. The agreement and intent for collaborative student placements between Seahaven and BCRH remains intact and the distance supervision clinical placement model will proceed given the opportunity.

BCRH aged care placements have also been impacted. Of 990 days of student placement booked in 2012, 640 of these placement days were cancelled by the student or education provider. In 2013, of 430 booked placement days, 120 days to date have been cancelled, a disappointing result given the time and effort the BCRH Education Department has put in to develop the program.

There has been collaborative/shared nursing and physiotherapy student placements between BCRH and BCCHS with very positive feedback from the students. Due to a vacancy in the BCCHS IT staff remote facilitation was not possible for these placements. There are further shared allied health and nursing placements planned for the second semester of 2013 (community placements are not generally requested in the first semester) and remote facilitation using the videoconference links between BCRH and BCCHS will be used for these student placements. In addition, BCCHS has employed a Graduate Nurse through the collaborative Expanded Care Graduate Program who commences June 2013 and distance supervision and mentoring will be provided to this nurse through both remote facilitation and face-to-face meetings as part of the collaborative between BCRH and BCCHS.

The refurbished student accommodation has been well received by students. The now open plan kitchen lounge area is a vast improvement on the previous arrangement. The new entrance has enabled the sleeping quarters to be separated from the living area which has improved both the privacy and sound dampening in the accommodation. The new beds, replacing the over twenty-year-old beds, are a significant improvement. As part of the refurbishment the rooms have also been wired for internet access for those students wishing to study in their rooms rather than accessing the learning space after hours. The accommodation that previously had only one shower and one toilet for ten occupants now has two bathrooms with toilets and a separate third toilet. The newly refurbished accommodation has been solidly booked since BCRH has commenced taking increased numbers of student.

# Key achievements for the period

Learning space works completed and area being utilised, utilisation rates measured,

Education precinct works completed enhancing student capacity,

Student accommodation refurbishment completed and being utilised,

Student placement offers exceeding project target, student placements commenced,

Seahaven aged care videoconferencing equipment operational and student placements arranged,

Student placements at BCCHS commenced,

Project completed,

Evaluation completed.

# Risks and mitigations strategies

| Identified risk/barrier | Mitigation strategy | Expected resolution date |
| --- | --- | --- |
| Nil |  |  |

# Expenditure to date

| Cost item | Budgeted expenditure | Actual expenditure (to date) |
| --- | --- | --- |
| Learning Space works and FFE | $74 670 | $90 272 |
| Upgrading student accommodation | $72 300 | $77 261 |
| Videoconferencing equipment – Purchase, installation and cabling | $22 708 | $21 320 |
| Computer – Purchase, installation and cabling | $2 200 | $1 818 |
|  | TOTAL (budgeted): | $171 878 | TOTAL (actual spend to date): | $190 671* |

*Budget overrun of $18 793 covered by a separate funding source. Total project cost for refurbishment of the student accommodation and the learning space exceeded budget by $20 563 however this overrun has been funded via savings achieved through reduced expenditure on computer and videoconferencing equipment ($1 770) and from a portion of the student accommodation upgrade being underwritten by a separate additional funding source ($20 000) secured to upgrade the bathroom area.

Key decisions to be made/actions to occur between now and 
project completion

Project finalised.

# Text boxes

Quarterly progress report

Small Capital and Equipment Program