Implementing a sustainable clinical 
supervision model

Project summary

This project aimed to implement a sustainable clinical supervision model across Eastern Metropolitan Clinical Placement Network (EMCPN). The project built upon the 2011 strategic pilot program entitled ‘Promoting a learning culture: Implementing a model to build confidence and skills of clinical supervisors’ where Teaching on the Run (TOTR) workshops were delivered to a range of health professionals within the EMCPN. The project delivered four additional TOTR Facilitator Training Program (FTP) workshops targeting aged care services, Aboriginal health services and medical practitioners. It will also support the participants from the pilot project to implement workshops in their organisations.

Drivers and challenges

Significant increases in professional entry university places and accompanying growth in demand for clinical placements require an increased number of skilled clinical supervisors. This growth in demand for clinical placements in an increasingly complex and changing clinical environment, together with workforce shortages and resource constraints, impacts on the ability and willingness of clinicians to take on additional student supervision. Supporting the increasing numbers of student health professionals completing clinical learning programs places a significant burden on education and clinical providers, in particular the health professionals given the responsibility to provide clinical supervision. A lack of adequate clinical supervision education and confidence in clinicians has proven to be a major barrier in increasing the quality and quantity of student placements across the health sector.

A priority for the EMCPN is to work in partnership with all sectors and disciplines across the network, to instil clinical education as core business and to increase supervision capacity. A review of the CPN ‘Data sets’ indicated that in 2010 both private organisations and public health services within the EMCPN provided a total of 98 965 clinical placement days to health professional students across a range of disciplines. From the facilities surveyed, the data also highlighted that the majority of clinical placement and education providers see the most important resource accessible by students during clinical placements is a placement supervisor/educator. Many facilities in the EMCPN indicated that approximately one to five staff is involved in the clinical supervision of health professional students, however there are also a significant number of facilities indicating that they have greater than 50 staff involved in the provision of clinical supervision. This data suggests that there is a significant number of staff across a range of disciplines within the EMCPN who are involved in the clinical supervision of students.

The clinical placement provider data, suggests that a number of staff across the disciplines have reported that formal training in education and supervision is available via internal or external courses, however quantifying the number of staff who have received formal training and/or the level and type of training is difficult. Furthermore, there still appeared to be significant number health facilities i.e., primary health care, some private and public health services and aged care services that identified no formal training courses are offered by their facilities.

With a track record of over ten years, the Teach Educate Learn Lead (TELL) Centre, a leader in clinical supervision education and support training programs for all health disciplines across all levels of training in Australia and internationally, was considered the most appropriate educational approach to address the issue of quality supervision within EMCPN. The TELL Centre programs are award winning, well established, have been nationally evaluated, include a suite of workshops focused on improving the skills of health professionals involved in clinical teaching, supervision and assessment and provide a significant range of educationally-based resources (including e-learning materials) to support ongoing development and sustainability of clinical supervisors.

In addition to the sound educational basis to utilise TELL Centre, the revisions undertaken by the TELL Centre to the TOTR FTP meant that workshops could be delivered in either standard format (3 to 3.5 hours duration per face-to-face workshop) or via the new blended learning format consisting of online preparation (30 minutes) plus one to two-hour face-to-face workshop. These options would provide additional flexibility to the planning, delivery mode and participant attendance at the workshops.

Arriving at a solution

The project involved the delivery of four TOTR FTPs to 48 health professionals across the EMCPN. TOTR was developed by the TELL Centre at the University of Western Australia initially to assist doctors increase their skills and confidence in teaching and supervising in the clinical environment. Continuing on from the 2011 strategic pilot program titled ‘Promoting a learning culture: Implementing a model to build confidence and skills of clinical supervisors’, this project offered additional support and a re-engagement session to participants from the pilot program (in particular, those who had not implemented any TOTR workshops) to implement TOTR workshops in their organisations.

The challenges of supporting health professional students are well documented. Real and perceived issues for clinical supervisors include balancing multiple roles and expectations whilst facilitating learning opportunities for students, a sense of inadequate preparation of student and supervisor and a lack of self confidence in providing feedback and assessment to students. The demand for support of student health professionals completing clinical learning programs continues to increase and place significant burden on educational providers and health care personnel. A lack of adequate educational preparedness and hence willingness of clinicians to undertake the role of clinical supervisor is a major barrier to health settings offering clinical placements for professional-entry students.

The Clinical Supervision Support Program (CSSP) of Health Workforce Australia (HWA) is detailed in HWA’s 2010 discussion paper. This paper discusses two examples of nationally evaluated clinical supervision training courses that have been developed and trialled for use with medical, nursing and allied health professions.

Our project implemented one of these programs, namely, TOTR. TOTR is a well-respected program that has been developed by the University of Western Australia and offered via the TELL Centre. The program has six modules, each designed to be delivered in either standard format (3 to 3.5 hours duration per face-to-face workshop) or via the new blended learning format consisting of online preparation (30 minutes) plus one to two-hour face-to-face workshop. There are also a range of practical teaching resources, including e-learning materials, web-based ‘Community of practice’ blogs which support the ongoing development and learning of clinical supervisors. The TOTR program was initially developed to assist doctors who had little or no teaching experience to increase their skills and confidence in teaching and supervising in the clinical environment. The program has been expanded to include a broader audience of health professionals including nurses, allied health professionals and veterinarians. Evaluation of the program by the TELL Centre indicates a significant increase in the confidence of participants to teach and supervise effectively, evaluation undertaken from this project support this finding.

This project involved conducting four TOTR FTPs, two at Deakin University in February and two at Inner East Melbourne Medicare Local (IEMML) in February and March 2013. Participants were targeted from aged care, medical and Aboriginal health services, as they had been identified from the evaluation data as not participating in the pilot project. Participants represented private and public hospital networks, non-government aged care facilities, community health services and GP divisions.

Participants of these four workshops took part in two full days of interactive training. The first half-day of training consisted of a TOTR clinical teaching workshop. This workshop aims to provide a small group training framework and involves exploring the role of facilitator within the clinical teaching setting. The TOTR FTP ran over the following one and a half days. The FTP workshop prepares participants to run TOTR workshops in their own settings, for their own colleagues and potentially a broader network of health professionals. Hence, once completed these workshops and attaining accreditation, a train the trainer model can be established.

Upon completion of the TOTR FTP, participants are provisionally accredited to deliver licensed TOTR workshops and are encouraged to run a TOTR workshop in their own setting within a year.

Following delivery of a TOTR Workshop and associated evaluations the participant becomes a level 1 fully accredited TOTR facilitator with ongoing access to TOTR resources via the TELL Centre. Facilitators will deliver TOTR workshops to groups of health professionals at their site, increasing the number of health professionals who have the confidence and skills necessary to support students during their clinical learning programs and a mechanism to provide sustainability of supervisors across EMCPN.

The other portion of the project was supporting participants from the pilot project to run TOTR workshops in their institutions. Eastern Health’s allied health service fully embraced the TOTR workshops with almost 100 per cent of their participants from the pilot project going on the deliver TOTR workshops. This involved physiotherapy, occupational therapy, dietetics, podiatry, social work and speech therapy. The majority of participants from the pilot project were from nursing and midwifery. Unfortunately this group encountered a number of challenges and issues in regards to implementing TOTR workshops following their initial attendance at the TOTR FTP workshop in the pilot project. To facilitate uptake of the TOTR workshops, two re-engagement sessions were offered to the nursing and midwifery staff from the pilot project. The aim of these sessions was to update participants of the changes to delivery modes (modules now available in a blended format) and to discuss strategies to address barriers and concerns. Only one of the re-engagement sessions was taken up by Eastern Health nursing and midwifery staff.

Implementation process

The project involved the delivery of four TOTR FTPs, targeting aged care services, medical practitioners and Aboriginal health services from the EMCPN. The TOTR program was developed as a staff development package by the TELL Centre at the University of Western Australia and aims to further develop the skills and confidence of health care professionals in their role of supervising students and prepare them to conduct TOTR workshops in their own organisation/network. TOTR FTP workshops were held at Deakin University and IEMML in February and March 2013. Support was also given to assist participants from the pilot project conducted in 2011-2012 to deliver TOTR workshops within their own workplace and attain level 1 accreditation.

TOTR FTP: the following resources were available to participants who attend the TOTR FTP workshops via the TELL Centre:

TELL Centre website: http://tellcentre.org/site/ ;

TOTR FTP guidebook;

TOTR teaching tips for clinicians.

TOTR workshops: participants of the TOTR workshops, following registration they were provided with access to the TELL Centre e-learning section of the TELL Centre website: http://elearning.tellcentre.org

Survey Monkey – three surveys

Outcomes and impacts

Across the EMCPN, 203 health professionals have completed the TOTR FTP. Of these participants, 41 have obtained level 1 fully accredited facilitator status; a further 10 have implemented strategies to offer workshops within their organisation, thereby will attain level 1 accreditation. It is envisaged that these 51 level 1 fully accredited facilitators will implement further workshops to groups of up to twenty staff members at their workplaces during the next 12 months.

Two level 1 fully accredited facilitators are working towards obtaining level 2 senior accredited facilitator status, one of which will achieve this outcome by end of July 2013.

This project has encouraged collaboration across disciplines and sectors within the EMCPN. This is evidenced by the:

Development of interprofessional teaching and learning teams who support quality clinical placements;

Student clinical experience being underpinned by a consistent supervision framework regardless of the discipline or setting;

Development of a sustainable training model that can continue to be delivered to additional staff on an ongoing basis, across the network and wider networks in general;

Accredited facilitators influencing others in the workplace to engage in the development of future health professionals in ways that create a positive learning environment.

The project has encouraged opportunities for increased clinical placements within expanded settings by the inclusion of health professionals from these settings attending TOTR FTP and subsequently gaining level 1 fully accredited facilitator status. This project has been timely, participants of TOTR are now educationally prepared, have the ability to provide quality supervision and a consistent supervision model is now becoming embedded across this sector.

In addition to the specific outcomes of the expanded setting sector, organisations across the EMCPN are now more open to the promotion of positive learning environments, have a greater awareness of the roles and responsibilities related to clinical supervision and have begun to embed a sustainable supervision workforce that provides opportunities for career development and succession planning.

A significant outcome was the inclusion of 14 medical practitioners in the TOTR FTP from both private practice and public health service. However, for the medical practitioners to maintain delivery of the TOTR workshops within their practice areas, support and time release from their responsibilities is needed to ensure sustainability from within this discipline.

Challenges and management strategies

| Risk | Management strategy | Outcomes |
| --- | --- | --- |
| Eastern Health nursing and midwifery facilitators not offering TOTR workshops. | Working closely with Eastern Health Director of Practice Development and Clinical Coordinator to identify barriers to offering workshops and providing support where permitted. | Re-engagement session Eastern Health 20 March 2013 with attendance of seven participants. A further session was offered in June but this was considered unnecessary by Eastern Health Nursing and Midwifery Clinical Coordinator. Project officer met with Clinical Coordinator and five nursing and midwifery staff in May to discuss TOTR processes, available resource updates and re-engaging participants and strategies to integrate more TOTR modules into Eastern Health’s preceptor education package. |
| Lack of participants for medical and Aboriginal health professionals TOTR FTP workshops scheduled for February and March 2013. | Discussion with reference group – extend medical workshop to include practice nurses. Flyers amended and resent to GP clinics. Further contact with Eastern Health, Director of Postgraduate Medical Education EH. Continue to work with key Aboriginal health professionals and/or those health professionals who supervise students within Aboriginal health areas and the Aboriginal executive committee member to increase participation in workshops scheduled for March 2013. Closing date for these workshops extended until December 2012. | 48 health professionals attended the four additional TOTR FTP workshops. Although the first three workshops registrations were initially at capacity, late cancellations and ‘no-shows’ resulted in lower attendance i.e.: 12, 14 and 15 respectively. Due to the late cancellations it was not possible for potential registrants on the waiting list to attend. The final workshop was identified for Aboriginal health professionals. Although strong initial interest was gained and a couple of registrations were received from Aboriginal health professionals, unfortunately no Aboriginal health professionals were able to attend. This workshop was subsequently offered to a wider audience, including any health professional who had contact with the Aboriginal health sector. Late cancellations for this workshop resulted in only seven participants attending. Following the workshop, contact was received from an Aboriginal health professional wanting to attend the next workshop; this person was directed to Northern Metropolitan CPN as a TOTR FTP was being offered via that network. |
| Not achieving level 2 status. | Discussions with TELL Centre, WA to negotiate pathway. | Two TOTR facilitators are progressing towards achieving level 2 senior accredited facilitator. One will complete final workshops in July and hence will achieve level 2 status. |
| Ability to capture all participant data required to complete report template for training. | Currently developing strategy to collect this data from previous and future participants via email template. Future reports will be updated to include this data where possible. | Strategy developed, emails sent to all participants with table to complete this data. The TELL Centre survey ‘tell us about yourself’, was also modified to include these questions. Low response from participants in completing this information. All data collected is included with this report. |

Conclusions

This project was able to build on the foundations of the pilot project ‘Promoting a learning culture: Implementing a model to build confidence and skills of clinical supervisors’, which had already begun to embed the TOTR workshops into organisations educational supervision structures. The ability to offer a consistent framework of training across disciplines and settings within EMCPN was recognised as a priority, implementing a program which has national recognition, underpinned by educational philosophy was also viewed as essential.

TOTR was selected as the most suitable model to support the educational needs of supervisors within the EMCPN. This program would not only provide health services across the network with a consistent approach to supervision and increase the quality of supervision practices, (as many supervisors across the network had no formal educational training) health professionals would have access to state-of-art resources hence creating efficiencies in time required to prepare and develop individual supervision training sessions.

This project has instigated significant collaboration across disciplines and settings, resulting in a more cohesive and open interprofessional supervision training model. It is expected that TOTR facilitators will become leaders in clinical education across the EMCPN, playing a pivotal role in implementing and maintaining a sustainable model of clinical supervision. Based on the outputs and impacts identified from this project, TOTR is well suited to be implemented across settings and disciplines as it supports all health professionals in their clinical teaching and supervision roles.

Evaluations of this project strongly suggest that participants have increased their overall knowledge, skills and equally as important their confidence in supervising students. This is reflected in participants’ comments regarding their willingness to engage in creating supportive learning environments, in providing structured feedback and their ability to identify impromptu teaching opportunities. Participants of TOTR no longer view students as burdens, rather as future health professionals who require quality experiences to develop the necessary core competencies of their individual professions.

A recommendation from this project is that the TOTR is a robust, practical and evidence-based supervision training program that will support quality supervision, facilitate excellence of teaching and a consistent approach to clinical supervision across settings and disciplines. For this approach to reach its full potential a further recommendation would be to appoint an overall coordinator to drive collaboration, organisation of workshops and maintain a data base; assist in breaking down the silos evident within the health sector and to facilitate dialogue between disciplines and settings.

Future directions and sustainability

This project built on the 2011 strategic pilot program titled ‘Promoting a learning culture: Implementing a model to build confidence and skills of clinical supervisors’, using TOTR. To ensure the TOTR program continues to thrive, there is a need for an overall independent coordinator to provide support, oversee the planning and implementation of TOTR workshops across disciplines and settings; to facilitate collaboration and communication between sectors and disciplines and to maintain the momentum and enthusiasm that has been established throughout the delivery of this project. An independent coordinator would provide the necessary support to sectors such as aged care which is not as well-resourced as other disciplines. An independent coordinator would also have the potential to encourage and facilitate interprofessional delivery of the TOTR workshops.

Smaller, private health sectors, such as the Medicare Locals provide significant opportunities for professional entry students to undertake clinical learning within these areas. To foster and encourage consistency of supervision practice across this sector, it is essential that these smaller providers are supported in their goals of offering TOTR training to cross sectoral disciplines. This would enable a greater degree of communication between diverse health care and collaboration.

The EMCPN now has a large number (749) of health care professionals who have taken part in the TOTR program through either the FTP or workshops. With the extension of the TELL Centre license to June 2015, TOTR will remain sustainable in the medium term. What happens after June 2015 will need to be carefully considered and aligned with the strategic direction of the CPN’s and Integrated Regional Clinical Training Networks (IRCTN) of Australia. Consideration of strategies that support mentoring, ongoing development of current facilitators and succession planning of future supervisors trained in TOTR philosophy will need to be implemented across EMCPN. Several CPN’s from within Victoria have also utilised TOTR as the educational program to support supervision practice, working collaborative across the CPN’s to share resources, support and maintain supervision training would be advantageous to the overall quality of supervision across Victoria, may facilitate further growth in clinical placements and would also have the potential to reduce supervision stress.

There is an opportunity for greater collaboration between Eastern and Northern CPN’s as both now have a level 2 accredited facilitator. These two facilitators are well placed to provide a ‘train the trainer’ model across both these networks and the other networks in general. Level 1 facilitators also need to be shared between disciplines and institutions enabling greater flexibility in delivering workshops and opportunities for collaboration.

Access to the TELL Centre website offers participants in TOTR a valuable resource to connect with people throughout Australia and overseas and to share information and learning’s. The Centre provides up-to-date, evidence-based resources for all workshop participants and facilitators, thereby reducing the necessity and time required in developing teaching and learning materials for supervision programs. The Centre also has an online forum known as the ‘community of practice’; this blog provides opportunities for facilitators and participants to engage in online discussions regarding supervision issues, current trends in practice or any other contemporary issue that participants wish to discuss. Hence, this community of practitioners are well connected to a wealth of resources and opportunities to continue in their supervision development.

This project has promoted the importance of developing a sustainable supervision workforce that enables students’ clinical experiences to be underpinned by a consistent supervision framework regardless of the discipline or setting. The long-term sustainability will depend on continued support from organisations who have participated in this project and the pilot project and their ability to work collaboratively with each other and share the resources available.

Further information

Di Welch, Director of Clinical Studies

School of Nursing and Midwifery, Faculty of Health

Deakin University

221 Burwood Highway, Burwood, Victoria 3125. Australia

Telephone: +61 3 9244 6599

Fax: +61 3 9244 6159

Email: dianne.welch@deakin.edu.au or: diannewelch@icloud.com

# Text boxes

Case study

Clinical Supervision Support Program